## Sprint-5 Status Summary
S.No | Type of User Story | US Title | API Team | UI Team | Data Team | ML Team | Testing Team | Comment
1 | Functional | DA_Map Sources_Form View - Multiple comments on DA form | 70% | 30% |  |  | 60% | Ready for Testing Date: 24-Sep-2021 20-Sep - Test cases completed
2 | Functional | DA_Define Domain _Form View_Submit Flow | 70% |  |  |  | 60% | Ready for Testing Date: 28-Sep-2021 Test Case due date: 27- Sep 24-Sep-2021: API development is completed 28-Sep - Test cases Completed
3 | Functional | DA_Define Domain_Form View _Save Flow | 70% |  |  |  | 60% | Ready for Testing Date: 28-Sep-2021 Test Case due date: 25- Sep 24-Sep-2021: API development is completed
4 | Functional | DA_Define Domain_Form View_Initial Load | 70% |  |  |  | 60% | Ready for Testing Date: 28-Sep-2021 Test Case due date: 26 -Sep 21-Sep - Test cases in Progress 22-Sep-2021: API development is completed 27-Sep - Test cases Completed
5 | Functional | DA_Define Domain_Form View_Cancel Button Flow | NA |  |  |  | 60% | Ready for Testing Date: 24-Sep-2021 Test Case due date: 21- Sep 21-Sep - Test cases completed
6 | Functional | DG_ Source Approval_List View | 100% | 100% |  |  | 100% | Ready for Testing Date: 22-Sep-2021 20-Sep - Test cases in Progress ( 80% Completed) - Due date 20- Sept 21-Sep - Test cases completed 21-Sep - API Development is completed 23- Sep - Testing in Progress ( 3 defects Identified) 27-Sep - Testing Completed
7 | Functional | DG_ Source Approval_Form View | 100% | 100% |  |  | 100% | Ready for Testing Date: 24-Sep-2021 Test Case due date: 23- Sep 21-Sep - Test cases in Progress (40%) 21-Sep - API Development is completed 22- Sep - Test Cases Completed 23- Sep - Testing in Progress 27-Sep - Testing Completed
8 | Functional | DG_ Source Approval _Form View_Approval Flow | 100% | 100% |  |  | 100% | Ready for Testing Date: 24-Sep-2021 Test Case due date: 22- Sep 21-Sep - Test cases in Progress (20%) 23- Sep - Test Cases Completed 22-Sep-2021: API development is completed 27-Sep - Testing Completed
9 | Functional | DG_ Source Approval_Form View _Save Flow | 100% | 100% |  |  | 90% | Ready for Testing Date: 24-Sep-2021 Test Case due date: 22- Sep 23- Sep - Test Cases Completed 22-Sep-2021: API development is completed 27-Sep - Testing in progress
10 | Functional | DG_ Source Approval_Form View_Cancel Button Flow | NA | 100% |  |  | 100% | Ready for Testing Date: 22-Sep-2021 20-Sep - Test cases in Progress ( 80% Completed)- Due date 20- Sept 21-Sep - Test cases completed 23- Sep - Testing Completed
11 | Functional | DSO_download attribute schema | 70% |  |  |  |  | Test Case due date: 23- Sep 17-Sep-2021: API development is completed 28-Sep - Test cases completed
12 | Technical | API_UI AWS Dev Environment Setup Script Creation | [5 empty] | 9/27/2021: The Code is moved to S3 From GIT
13 | Technical | Data_ Creating Configurable Code for Standardization and S3 Bucket Configuration (From Sprint 4) |  |  | 80% |  |  | 22-Sep: Code review in Progress
14 | Technical | Data_ Development of GRAD rules (From Sprint 4) |  |  | 90% |  |  | 22-Sep: Code Development Completed, unit testiing and Code review by Spint 5
15 | Technical | Data_ Creation/Update of Golden Record |  |  | 10%
16 | Technical | ML_Finalize the combination of the model, imputation strategy and feature engineering strategy (Extended from Sprint 3) |  |  |  | 55% |  | 13-Sep: Dependency of IEEE Feedback on the proposed labeled Data 17-Sep Available Labeled Record : 8500
17 | Technical | Ml_Testing ML model deployment infrastructure on EKS Fargate (From Sprint 4) | [5 empty] | 13-Sep: Dependency with the EKS Fargate Environment setup, To check using Saegmaker and step function (with AWS Support Team) To Check on the Direct AWS Direct Contact Email, To Check using Lambda function To Check on Schedule Container For EKS Fargate To Check with IEEE to use AWS Batch- IEEE Demo on AWS Batch on EKS by Vijay and the Access will be grant in Dev1
18 | Technical | ML_Based on Grouping strategy create labelled data & send it to IEEE for auditing (Extended from Sprint 3) |  |  |  | 70% |  | 13-Sep: Completed 19 Albhebet for this Sprint - Remaing 7 Will be Complete in next Sprint 24-Sep: 3 mORE Alphabet to complete ETA By 28-Sep
19 | Technical | ML_EDA on labelled data |  |  |  | 70% |  | 22-Sep Merge to Notebook by Today

## Issues_List
S.No | Issue | Team | Status | Comment
1

## ML Task
User Story | Task | Estimated Effort | Status | Assigned To | Comment | Description
ML_Finalize the combination of the model, imputation strategy and feature engineering strategy (Extended from Sprint 3) |  | 90hours | Not Started | Trina De
| Create different versions of script for testing | 65 (Completed) | 15% |  | Dependency : IEEE should start sending back the labelled data to LTI Team after approve/update which will be used for ML/DL model training. Expected to Receive From IEEE on or before 10 Aug | Here we will be creating the code that is needed to finalize the model, the data preprocessing strategy and the imputation strategy.
| Finalize ML model | 25 |  |  |  | • We will also try different models. We will create a report to understand how the ML model is performing in the presence of null values. This will help us to finalize the combination of the model, imputation strategy and feature engineering technique. • We will share this analysis with IEEE and make sure LTI and IEEE both agree on it.
| Finalize imputation and feature engineering strategy | 25 |  |  |  | • Post IEEE review, the labelled data will be used for Model training. We will continue this process till we get sufficient data (20,000 records per source). • After getting labelled data, we will create a simple ML model and try different imputation strategies for the null values and different feature engineering techniques to finalize our imputation strategy and feature engineering technique.
| Creating scripts for cleaning labelled data | 15 |  |  |  | Here we will be creating the script that will filter the data we receive from IEEE based on invalid values in columns.
ML_Testing ML model deployment infrastructure on EKS Fargate |  | 45 hours | Not Started | Trina De
| Researching about Fargate environment and related requirements | 10 |  |  |  | Read up about Fargate and how it works in conjunction with AWS EKS
| Creating code repository with all requirements for the docker container | 10 |  |  |  | Setup of directory that has our requirements and sample inference code, code specific changes for Fargate
| Testing in an environment similar to the actual deployment environment | 25 |  |  |  | • Testing and debugging model inference pipeline on Fargate. • Testing the scheduling of tasks on the container (batch processing). • Testing performance(time) of the container. • Testing concurrency and timeout of tasks on this container.
ML_Based on Grouping strategy create labelled data & send it to IEEE for auditing (Extended from Sprint 3) |  | 135hours | In-Progress | Roseline Gounder, Yash Shah
| Labeling of remaining 7 letters |  |  |  |  | We will be taking up the letters remaining for processing from Sprint 4
| Updating pipeline as per requirements from IEEE |  |  |  |  | We will be updating our pipeline if there are any major change requirements from IEEE.
EDA on labelled data |  | 85hours | In-Progress | Trina De, Yash Shah, Roseline Gounder
| Getting meaningful insights from labelled data |  | 15% |  |  | • Write code to filter and format the labelled data received from IEEE • Write code to generate graphs on the labelled data • Use the graph to get meaningful insights which will aid in feature engineering • Determining relationship between numerical features • Labelling of records alongside IEEE

## Data Task
S.no | User Story | Task | Estimated Effort | Status | Assinged To | Comment
1 | Creating Configurable Code for Standardization and S3 Bucket Configuration | Merging and Applying the Grouping Logic for Editor, Reviewer, Siebel and Author Source for 3 more Alphabet |  | Completed | Vibhuti | 17-Sep: Blue Highlighted one is Completed as part of Print 4
2 |  | Create a Connection with S3 Bucket | 4 | Completed ( With Local Setup) | Hoshang | Dependency: S3 bucket and connection details(access & secret Key/IAM role) and lambda details along with role. 25-Aug: Yet to Receive the S3 Dev 1 Bucket Details
3 |  | Write the file to Error S3 bucket and send email to Source owner(DSO details to be passed as configuraiton for email) | 27 | Completed ( With Local Setup) | Ashish | IEEE will provide the email id(For each environment) for sending the notification and will agree on the template for mail IEEE will provide the S3 bucket location for placing the error file for each source
4 |  | Develop a code to write the Error records in error file back in S3 and alert the DSO |  | Completed ( With Local Setup) | Ashish | Dependency: S3 bucket and connection details(access & secret Key/IAM role).
5 |  | Once CSV file is found, file level validations for File Size, record counts, file extension and Naming convention should be performed for each thread independently(parallel execution for each source) Includes S3 Configuration | 36 | Completed ( With Local Setup) | Shweta | Dependency: S3 bucket and connection details(access & secret Key/IAM role) and lambda details along with role. Code development is completed with local csv file. Testing is pending.
6 |  | Develop a code to create the file/dataframe from the standardized record for ML Model consumption for Address, Organization and Phone No | 36 | Completed | Shweta | Develop a generic code to standardize the records for organization,phone number and address multivalue columns.
7 |  | Take the Delimiter value for each source from the source registration and validate in the prevalidation script. | 18 | Completed ( With Local Setup) | Hoshang
8 |  | To Check the source file in the Particluar folder e.g. siebel should contain file named Sieble_<TimeStamp>.csv | 27 | Completed ( With Local Setup) | Hoshang
9 |  | Data level validation null check for mandatory columns after standardization | 5 | Completed | Priya
10 |  | Merge all resultant source level files to one json file | 36 | Completed | Priya/Naveen
11 |  | Creation of Post standarization Error file | 36 | Completed | Naveen/Priya
12 |  | Code Migration from pyspark to Python includes Grouping file handing code Changes |  | Completed | Vibhuti | 27-sep - Code Development completed - Yet to code review
|  | Grouping Logic update |  | In progress | Vibuthi
13 |  | Develop a code to read configurations and perform standardization accordingly by calling respective functions for Address,Organization and Phone No | 18 | Completed | Priya
14 |  | Create mapping files from mongodb | 16 | Completed | Naveen
15 |  | Create a Mongo/Document DB Collection/parameter file for storing configuration parameters(source registration) | 5 | Completed | Priya/Saurabh
16 |  | Create the configurable code to generate the file for ML input |  | Completed | Naveen/Priya
|  | Unit Test Case creation |  | In progress | Naveen/Priya/Ashish/Hoshang/Swetha
17 | Code Development to define standard input structure into JSON format | Create a configurable code to form JSON complex structure with sourceMapping | 100 | Completed | Naveen/Priya
18 | Data_ Development of GRAD rules | Develop a function source_priority to implement grad rule. Step 1- Grad rule collection will be created. Step 2- Rule name will be fetched from the collection for the particular attribute and function will be processed. Step 3- It will return the final value for the particular attribute as a result. | 27 | Completed | Hoshang
19 |  | Develop a function ALLvalues to implement grad rule. Step 1- Grad rule collection will be created. Step 2- Rule name will be fetched from the collection for the particular attribute and function will be processed. Step 3- It will return the final value for the particular attribute as a result. | 27 | Completed | Ashish
20 |  | Develop a function Y_if_1_Y to implement grad rule. Step 1- Grad rule collection will be created. Step 2- Rule name will be fetched from the collection for the particular attribute and function will be processed. Step 3- It will return the final value for the particular attribute as a result. | 27 | Completed | Vibhuti
| CR | Develop a function Sum of All to implement grad rule. Step 1- Grad rule collection will be created. Step 2- Rule name will be fetched from the collection for the particular attribute and function will be processed. Step 3- It will return the final value for the particular attribute as a result. |  | Completed | Vibhuti
21 |  | Develop a function N_if_1_N to implement grad rule. Step 1- Grad rule collection will be created. Step 2- Rule name will be fetched from the collection for the particular attribute and function will be processed. Step 3- It will return the final value for the particular attribute as a result. | 27 | Completed | Shweta
22 | Data_ Creation/Update of Golden Record | Development of GRAD rule engine that will Identify the GUID set for which Golden record needs to be recalculated or created
23 |  | Development of GRAD rule engine that will Be configurable for the identification of Golden record attributes
24 |  | Development of GRAD rule engine that will Read in the domain parameters and identify the GUID sets for which GRAD rules need to be run
25 |  | Development of GRAD rule engine that will Get the values for each attribute of Golden record from the reusable GRAD rules functions
26 |  | Development of GRAD rule engine that will Join all the attributes values for form a complete golden record for a domain | 54 | Completed | Naveen/Priya
27 |  | Once the golden record is created out of the GUID set insert or update the Golden Record repository

## UI Task
User Story | Task | Estimated Effort | Status | Assigned To | Comment
DA_Map Sources_Form View - Multiple comments on DA form | multicomment attribute level and form level layout | 6 |  | Laxman | Due Date : -24-Sep-2021
| DA multicomment validations | 8
| DSO multicomment validations | 8
| save/submit/cancel button multicomment validations | 12
| api integration | 12
| unit testing | 4
DA_Define Domain _Form View_Submit Flow |  |  |  | Anmol | Due Date : -28-Sep-2021
| submit button display validations | 6
| submit button mandatory fields error scenarios | 12
| submit button success scenarios | 4
| api integration | 12
| unit testing | 4
DA_Define Domain_Form View _Save Flow |  |  |  | Laxman | Due Date : -28-Sep-2021
| dynamically enable/disable save button | 6
| validations for signle valued attribute checkbox | 8
| confirm and cancel popup validations | 12
| validations for mandatory fields | 16
| api integration | 6
| unit testing | 4
DA_Define Domain_Form View_Initial Load |  |  |  | Anmol | Due Date : -28-Sep-2021
| New module, routing, services and component layout for Form view | 8
| form level comment and attribute table mapping | 8
| attribute table validations | 12
| upload xls file | 6
| singlevalued checkbox validations | 6
| api integration and toster messages | 30
| Unit testing | 6
DA_Define Domain_Form View_Cancel Button Flow |  |  |  | Rahul | Due Date : -24-Sep-2021
| add cancel button | 4
| enable/disable cancel button | 8
| api integration and cancel attribute grid | 6
| unit testing | 2
DG_ Source Approval_List View |  |  |  | Niveda | Due Date : -22-Sep-2021
| list view component/routing/module crreation | 4
| sorting/searching feature | 4
| list view grid implementation | 4
| api integration | 6
| unit testing | 2
DG_ Source Approval_Form View |  |  |  | rahul | Due Date : -24-Sep-2021
| New module, routing, services and component layout for Form view | 4
| form level comment and attribute table mapping | 8
| attribute table validations | 8
| domain level 1 and 2 popup confirmation | 6
| reject/approve workflow | 6
| api integration and toster messages | 4
| Unit testing | 4
DG_ Source Approval _Form View_Submit Flow |  |  |  | Niveda | Due Date : -24-Sep-2021
| submit button display validations | 6
| submit button mandatory fields error scenarios | 12
| submit button success scenarios | 4
| api integration | 6
| unit testing | 2
DG_ Source Approval_Form View _Save Flow |  |  |  | Niveda | Due Date : -24-Sep-2021
| dynamically enable/disable save button | 4
| validations for signle valued attribute checkbox | 6
| confirm and cancel popup validations | 4
| validations for mandatory fields | 6
| api integration | 8
| unit testing | 2
DG_ Source Approval_Form View_Cancel Button Flow |  |  |  | Rahul | Due Date : -22-Sep-2021
| add cancel button | 2
| enable/disable cancel button | 4
| api integration and cancel attribute grid | 2
| unit testing | 1

## API Task
li
User Story | Task | Estimated Effort | Status | Target Date | Assigned To | Comment
Multiple comments on DA form | API Analysis | 8 | Completed |  | Tirth
| API Development | 32 | In Progress |  | Tirth
| Unit Testing and code coverage | 8 | Yet to Start |  | Tirth
| Code / Peer review | 4 | Yet to Start |  | Rajesh
| SONAR issues fixing for code quality | 4 | Yet to Start |  | Tirth
| UI Integration and Testing | 8 | Yet to Start |  | Tirth
DA_Define Domain _Form View_Submit Flow | API Analysis |  | Completed |  | Rajesh
| API Development |  | Completed |  | Rajesh
| Unit Testing and code coverage |  | Yet to Start |  | Pranali
| Code / Peer review |  | Yet to Start |  | Tirth
| SONAR issues fixing for code quality |  | Yet to Start |  | Rajesh
| UI Integration and Testing |  | Yet to Start |  | Rajesh
DA_Define Domain_Form View _Save Flow | API Analysis |  | Completed |  | Rajesh
| API Development |  | Completed |  | Rajesh
| Unit Testing and code coverage |  | Yet to Start |  | Pranali
| Code / Peer review |  | Yet to Start |  | Tirth
| SONAR issues fixing for code quality |  | Yet to Start |  | Rajesh
| UI Integration and Testing |  | Yet to Start |  | Rajesh
DA_Define Domain_Form View_Initial Load | API Analysis |  | Completed |  | Rajesh
| API Development |  | Completed |  | Rajesh
| Unit Testing and code coverage |  | Yet to Start |  | Pranali
| Code / Peer review |  | Yet to Start |  | Tirth
| SONAR issues fixing for code quality |  | Yet to Start |  | Rajesh
| UI Integration and Testing |  | Yet to Start |  | Rajesh
DG_ Source Approval_List View | API Analysis |  | Completed |  | Dharmendra
| API Development |  | In Progress |  | Dharmendra
| Unit Testing and code coverage |  | Yet to Start |  | Dharmendra
| Code / Peer review |  | Yet to Start |  | Rajesh
| SONAR issues fixing for code quality |  | Yet to Start |  | Dharmendra
| UI Integration and Testing |  | Yet to Start |  | Dharmendra
DG_ Source Approval_Form View | API Analysis |  | Completed |  | Dharmendra
| API Development |  | In Progress |  | Dharmendra
| Unit Testing and code coverage |  | Yet to Start |  | Dharmendra
| Code / Peer review |  | Yet to Start |  | Rajesh
| SONAR issues fixing for code quality |  | Yet to Start |  | Dharmendra
| UI Integration and Testing |  | Yet to Start |  | Dharmendra
DG_ Source Approval _Form View_Submit Flow | API Analysis |  | Completed |  | Dharmendra
| API Development |  | Yet to Start |  | Dharmendra
| Unit Testing and code coverage |  | Yet to Start |  | Dharmendra
| Code / Peer review |  | Yet to Start |  | Rajesh
| SONAR issues fixing for code quality |  | Yet to Start |  | Dharmendra
| UI Integration and Testing |  |  |  | Dharmendra
DG_ Source Approval_Form View _Save Flow | API Analysis |  | Completed |  | Dharmendra
| API Development |  | Yet to Start |  | Dharmendra
| Unit Testing and code coverage |  | Yet to Start |  | Dharmendra
| Code / Peer review |  | Yet to Start |  | Rajesh
| SONAR issues fixing for code quality |  | Yet to Start |  | Dharmendra
| UI Integration and Testing |  |  |  | Dharmendra
DSO download attribute schema | API Analysis |  | Completed |  | Tirth
| API Development |  | Completed |  | Tirth
| Unit Testing and code coverage |  |  |  | Tirth
| Code / Peer review |  | Completed |  | Rajesh
| SONAR issues fixing for code quality |  |  |  | Tirth
| UI Integration and Testing |  |  |  | Tirth

## Testing Task
User Story | Task | Estimated Effort in Hrs | Status | Assigned To | Comment
DA_Map Sources_Form View - Multiple comments on DA form |  |  |  | Ashish
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 6 | Completed
| QA_Testing_Test Case Review | 2 | In Progress
| QA_Testing_Test Execution and Defect Tracking | 12 | Not Started
DA_Define Domain _Form View_Submit Flow |  |  |  | Priya
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Not Started
| QA_Testing_Test Case Review | 2 | Not Started
| QA_Testing_Test Execution and Defect Tracking | 12 | Not Started
DA_Define Domain_Form View _Save Flow |  |  |  | Sushil
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Not Started
| QA_Testing_Test Case Review | 2 | Not Started
| QA_Testing_Test Execution and Defect Tracking | 12 | Not Started
DA_Define Domain_Form View_Initial Load |  |  |  | Priya
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 12 | Not Started
DA_Define Domain_Form View_Cancel Button Flow |  |  |  | Priya
| QA_Testing_Requirement Analysis | 2 | Completed
| QA_Testing_Test Case Creation | 4 | Completed
| QA_Testing_Test Case Review | 2 | Not Started
| QA_Testing_Test Execution and Defect Tracking | 6 | Not Started
DG_ Source Approval_Form View |  |  |  | Ashish
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Completed |  | 100% Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 12 | Completed
DG_ Source Approval_List View |  |  |  | Sushil
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 12 | Completed
DG_ Source Approval _Form View_Approval Flow |  |  |  | Sushil
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 8 | Completed |  | 100% Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 12 | Completed
DG_ Source Approval_Form View _Save Flow |  |  |  | Ashish
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 5 | Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 12 | Completed
DG_ Source Approval_Form View_Cancel Button Flow |  |  |  | Priya
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 6 | Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 8 | Completed
DSO_download attribute schema |  |  |  | Priya
| QA_Testing_Requirement Analysis | 4 | Completed
| QA_Testing_Test Case Creation | 5 | Completed
| QA_Testing_Test Case Review | 2 | Completed
| QA_Testing_Test Execution and Defect Tracking | 8 | Not Started